## Sheet1
User Stories | Allocated Sprints | Fibinacci Difficulty Score | Dependencies
As a user I want to be able to play on a traditional 3x3 grid | Sprint 1 | 2 | UI Mockup
As a user, I would like to be able to have directions on how to play the game | Sprint 1 | 1 | 3x3 Grid
As a developer I would like to have everyone's UML or UI diagrams in one place, so they are easy to submit and view in one place. | Sprint 1 | 1 | UMLs and UIs
As a user, I would like to be able to play against the computer | Sprint 1 | 5 | Player Interface
We will need to allow the user to place the character. Meaning once a button is clicked X or O will be displayed. | Sprint 1 | 3 | Player and CPU player classes
--------------------------------------------------------------------------------------------
As a user I want to keep track of how many times I win vs how many times the Computer wins. | Sprint 2 | 3 | check game class
As a user, I would like the game to automatically clear, so I don't have to press "new game" or restart each time. | Sprint 2 | 3 | Check Game class
As a user, I would like to be able to start a new game without having to close out the program, enabling me to keep the current scoreboard. | Sprint 2 | 1 | Game Count Class, Check Game class
As a user, I would like the game to decipher who has won when each game ends | Sprint 2 | *8 | Game Count Class
Practical Fibonacci Difficulty Scores:
0 | No effort is Required
1 | Extra Small: Developers feel they understand most requirements and consider it relatively easy, likely completed in one day.
2 | Small: A little bit of thought, effort, or problem solving is required, be developers have done this a lot. Sounds maybe extra small, but want to hedge the bets a little.
3 | Average: Developers have done this a lot; they know what needs to be done. There may be few extra steps, but it is doubtful that any research will need to be done to complete the task.
5 | Large. This is complex work or it is unfamiliar and the developers will need the help of others on the team. Some research may be required. This would be the largest item in a single sprint.
8 | Extra Large: This is going to take some time and research and probably more than one develper to complete. In addtion, Developers need to make several assumptions and this will increase risk and could affect getting it done.
13 | WARNING!! This is a complex piece of work with a lot of unkowns and requires multiple assumptions to size. It is too much to complete in one sprint. Instead, split this into multiple itmes that can be completed independently.
21 | 21 or 34 reflects too much complexity to be done within one Sprint. It will need to be refined more. The large size also indicates more risk, assumptions, and dependencies involved to complete this item.